## Sheet1
Thesis Schedule

Completion Date:	Aug 18	Aug 25	Sept 1	Sept 8	Sept 15	Sept 22	Sept 29	Oct 06	Oct 13	Oct 20	Oct 27	November 3rd

THESIS DUE					X

Ch1 (Intro)	X
Ch2 (ANITA)		X
Ch3 (Calibration)			X
Ch5 (Cosmic Ray Search)				X
Ch4 (Simulation)					X
Ch6 (Results)					X
Ch7 (Conclusion)					X

Blinding Strategy	X
Unblinding Request		Delayed →	Delayed →	Delayed →	Monday Sept 18th
Results of Unblinding			Delayed →	Delayed →	X

Revisions					X	X	X	X	X

Defense					X

Key:	Complete	Pending Comments	To Do